## Project Plan and Gantt
Project Name | Product Release
Project Manager | Alex B.
Project Deliverable
Scope Statement:
Start Date | 2016-08-19
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Nguyễn Đức Tài | 2016-09-03 | 2016-09-04 | 1 | Complete
Agree on objectives | Nguyễn Đức Tài | 2016-09-03 | 2016-09-04 | 1 | Complete
Detailed Reqs. | Nguyễn Đức Tài | 2016-09-03 | 2016-09-04 | 1 | Complete
Techincal Reqs. | Nguyễn Tuấn Anh | 2016-09-03 | 2016-09-04 | 1 | Complete
DB Development | Trần Trường An | 2016-09-05 | 2016-09-10 | 5 | Complete
Form AppQLGiay | Nguyễn Tuấn Anh | 2016-09-11 | 2016-09-15 | 4 | Complete
select/update/insert | Trần Trường An | 2016-09-16 | 2016-09-22 | 6 | Complete
Connection DB | Nguyễn Đức Tài | 2016-09-23 | 2016-10-05 | 12 | in-progress
Thêm | Nguyễn Tuấn Anh | 2016-09-23 | 2016-10-05 | 12 | in-progress
Sửa | Nguyễn Tuấn Anh | 2016-09-23 | 2016-10-05 | 12 | in-progress
Xóa | Nguyễn Tuấn Anh | 2016-09-23 | 2016-10-05 | 12 | in-progress
Tiềm kiếm | Nguyễn Tuấn Anh | 2016-09-23 | 2016-10-05 | 12 | in-progress
Testing | Nguyễn Đức Tài | 2016-10-05 | 2016-10-07 | 2 | Not started
Connect Webservice | Nguyễn Tuấn Anh | 2016-10-08 | 2016-10-09 | 1 | Not started
Kiểm tra hoàn tất | Tài, Anh, An | 2016-10-10 | 2016-10-10 | 0 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Nguyễn Đức Tài | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document | nguyenductai10d@gmail.com
Nguyễn Tuấn Anh | Developer | 1. Design GUI/database. 2. Code. 3. Test | Trantruongan603@gmail.com
Trần Trường An | Developer | 1. Design GUI/database. 2. Code. 3. Test | onlyanh2014@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team